## test planing and info.
|  | Project Name : | Tap Cash (ODC)
|  | Team | 5.dev
|  | Designed By : | Ahmed Helmy Mohamed
|  | reviewed by : | Ahmed Helmy Mohamed
|  | Test Design Date : | 29/4/2023
|  | Delivery Date | 2023-10-05
|  | Browser : | Chrome
|  | windows | 10
Android Version
IOS Version
- main features : | 1- Authentication (sign up - sign in+ first use- forget password )
2- home page
3- wallet
4-dash board
5- sub account (children)
- test suites : | 1-sign up
2-sign in
3-forget password
4-home page
5- wallet
6-dash board
7-more
- Manual testing
- test cases for each test suite with all expected Scenarios
- Early testing with test design
- test execution after back end deliver his work
- Manual API testing with report
- Design Bug report
- Design summary report

## API testing
- API testing
- Authentication function
- Environment : (windows - postman tool)
- API testing
- Get registed user
- Environment : (windows - postman tool)
- API testing
- Wallet function
- Environment : (windows - postman tool)
- API testing
- Smart card function
- Environment : (windows - postman tool)
- API testing
- Add credit card function
- Environment : (windows - postman tool)

## Bug report
- only sign up execution delivered from developers |  | Bug report
- network : wifi / mobile data
- Environment : (windows - chrome browser - Android)
ID | Title | Steps | Expected result | Actual result | periority | screen shoot
Tap_ts1tc1 | - verify sign up button on web app. on home page | 1- open website url page 2- search for sign up button on home page to click on | - website opened - find sign up button to redirect to sign up page | - website opened - cant find sign up button on home page | medium
ID | Title | Steps | Expected result | Actual result | periority | screen shoot
Tap_ts1tc4.2 | - verify create password function with invalid conditions of password (web app.) | 1-open website page 2-click on sign up button 3-write your valid mobile number 4-click on continue button 5-wait for pin msg sent to ur number 6-enter sent code in code field 7-click on verify button 8-enter invalid password 9-enter invalid confirm password 10-select remember me option 11-click on continue button | - website opened - redirect to sign up page - mobile number is entered - redirect to verification page - pin msg sent - filled in with pin code - redirect to next page - invalid password is entered - confirm password is written - remember me option is selected - wrong msg with enter your valid password" | - website opened - redirect to sign up page - mobile number is entered - redirect to verification page - pin msg sent - filled in with pin code - redirect to next page - invalid password is entered - confirm password is written - remember me option is selected - Sign up successful! | high
ID | Title | Steps | Expected result | Actual result | periority | screen shoot
Tap_ts1tc2 | - verify contiue button with valid mail on mobile app | 1-open mobile app. 2-click on sign up button 3-write your valid mail 3-click on continue button | - mobile app. opened - redirect to sign up page - mail is entered - redirect to verification page | - mobile app. opened - redirect to sign up page - mail is entered - loading without redirect to next page | high

## 1-sign up
- Test suite : sign up
- Test suite ID : TS1
- Environment : (windows - android - IOS)
- pre-condition : open URL/ APP.
1- verify sign up button
steps | action | expected | status | test data | req.id | bug.id
1.1 | open ( website page/app) | - website opened | pass |  | TS1_TC1 | Tap_ts1tc1
1.2 | click on sign up button | - redirect to sign up page | fail
2- verify contiue button with valid mail
steps | action | expected | status | test data | req.id | bug.id
2.1 | open ( website page/app) | - website opened |  | mail: helmyahmed1993@gmail.com | TS1_TC2 | Tap_ts1tc2
2.2 | click on sign up button | - redirect to sign up page
2.3 | write your valid mail | - mail is entered
2.4 | click on continue button | - redirect to verification page | fail
2.1- verify contiue button with invalid mail
2.1.1 | open sign up page | - redirect to sign up page |  | mail: helmyahmed1993 | TS1_TC2.1
2.1.2 | write your invalid number | - invalid mobile number is entered
2.1.3 | click on continue button | - display error message enter valid mail
2.2- verify contiue button with empty field
2.2.1 | open sign up page | - redirect to sign up page |  | mail: empty | TS1_TC2.2
2.2.2 | let your mail field empty | - mail field is empty
2.2.3 | click on continue button | - display error message enter your number
3- verify valid verification code function
steps | action | expected | status | test data | req.id | bug.id
3.1 | open ( website page/app) | - website opened |  | mail: helmyahmed1993@gmail.com sent ver. code | TS1_TC3
3.2 | click on sign up button | - redirect to sign up page
3.3 | write your valid mail | - mail is entered
3.4 | click on continue button | - redirect to verification page
3.5 | wait for pin msg sent to ur number | - pin msg sent
3.6 | enter sent code in code field | - filled in with pin code
3.7 | click on verify button | - redirect to next page
3.1- verify invalid verification code function
steps | action | expected | status | test data | req.id | bug.id
3.1 | open ( website page/app) | - website opened |  | mail: helmyahmed1993@gmail.com invalid sent ver. code | TS1_TC3.1
3.2 | click on sign up button | - redirect to sign up page
3.3 | write your valid mail | - mail is entered
3.4 | click on continue button | - redirect to verification page
3.5 | wait for pin msg sent to ur number | - pin msg sent
3.6 | enter invalid code in code field | - filled in with invalid pin code
3.7 | click on verify button | - display msg of invalid code
3.2- verify verification code function with empty field
steps | action | expected | status | test data | req.id | bug.id
3.2.1 | open ( website page/app) | - website opened |  | mail: helmyahmed1993@gmail.com sent ver. code = empty | TS1_TC3.2
3.2.2 | click on sign up button | - redirect to sign up page
3.2.3 | write your valid mail | - mail is entered
3.2.4 | click on continue button | - redirect to verification page
3.2.5 | wait for pin msg sent to ur number | - pin msg sent
3.2.6 | let pin field empty | - pin field is empty
3.2.7 | click on verify button | - display msg of enter valid code
3.3- verify verification code function if pin msg didnot send
steps | action | expected | status | test data | req.id | bug.id
3.3.1 | open ( website page/app) | - website opened |  | mail: helmyahmed1993@gmail.com | TS1_TC3.3
3.3.2 | click on sign up button | - redirect to sign up page
3.3.3 | write your valid mail | - mail is entered
3.3.4 | click on continue button | - redirect to verification page
3.3.5 | wait for pin msg sent to ur number | - pin msg didnot send
3.3.6 | click on resend button | - pin msg sent
3.3.7 | click on verify button | - redirect to next page
4- verify create password function with valid data
steps | action | expected | status | test data | req.id | bug.id
4.1 | open ( website page/app) | - website opened | pass | mail: helmyahmed1993@gmail.com pass: 123456#Ah (min. 8 ch. with capital letter and symbol) | TS1_TC4
4.2 | click on sign up button | - redirect to sign up page
4.3 | write your valid mail | - mobile number is entered
4.4 | click on continue button | - redirect to verification page
4.5 | wait for pin msg sent to ur mail | - pin msg sent
4.6 | enter sent code in code field | - filled in with pin code
4.7 | click on verify button | - redirect to next page
4.8 | create your password | - password field is filled in entered pass.
4.9 | rewrite your choosen pass. in confirm pass. field | - confirm password field is filled with pass.
4.1 | select remember me option | - remember me option is selected
4.11 | click on continue button | - redirect to ID num. page
4.1- verify create password function without remember me function
steps | action | expected | status | test data | req.id | bug.id
4.1.1 | open ( website page/app) | - website opened |  | mail: helmyahmed1993@gmail.com pass: 123456#Ah (min. 8 ch. with capital letter and symbol) | TS1_TC4.1
4.1.2 | click on sign up button | - redirect to sign up page
4.1.3 | write your valid mobile number | - mobile number is entered
4.1.4 | click on continue button | - redirect to verification page
4.1.5 | wait for pin msg sent to ur number | - pin msg sent
4.1.6 | enter sent code in code field | - filled in with pin code
4.1.7 | click on verify button | - redirect to next page
4.1.8 | create your password | - password field is filled in entered pass.
4.1.9 | rewrite your choosen pass. in confirm pass. field | - confirm password field is filled with pass.
4.1.10 | do not select remember me option | - remember me option is selected
4.1.11 | click on continue button | - redirect to ID num. page
4.2- verify create password function with invalid data
steps | action | expected | status | test data | req.id | bug.id
4.2.1 | open ( website page/app) | - website opened | pass | pass: 1234 | TS1_TC4.2 | Tap_ts1tc4.2
4.2.2 | click on sign up button | - redirect to sign up page | pass
4.2.3 | write your valid mobile number | - mobile number is entered | pass
4.2.4 | click on continue button | - redirect to verification page | pass
4.2.5 | wait for pin msg sent to ur number | - pin msg sent | pass
4.2.6 | enter sent code in code field | - filled in with pin code | pass
4.2.7 | click on verify button | - redirect to next page | pass
4.2.8 | enter invalid password | - invalid password is entered | pass
4.2.9 | enter invalid confirm password | - confirm password is written | pass
4.2.10 | select remember me option | - remember me option is selected | pass
4.2.11 | click on continue button | - wrong msg with enter your valid password | fail
5- verify create ID number
steps | action | expected | status | test data | req.id | bug.id
5.1 | open ( website page/app) | - website opened | pass | mail: helmyahmed1993@gmail.com pass: 123456#Ah (min. 8 ch. with capital letter and symbol) ID : 29306041522289 | TS1_TC5
5.2 | click on sign up button | - redirect to sign up page
5.3 | write your valid mail | - mobile number is entered
5.4 | click on continue button | - redirect to verification page
5.5 | wait for pin msg sent to ur mail | - pin msg sent
5.6 | enter sent code in code field | - filled in with pin code
5.7 | click on verify button | - redirect to next page
5.8 | create your password | - password field is filled in entered pass.
5.9 | rewrite your choosen pass. in confirm pass. field | - confirm password field is filled with pass.
5.1 | select remember me option | - remember me option is selected
5.11 | click on continue button | - redirect to ID num. page
5.12 | enter your valid id number | - valid id is entered
5.13 | click on sign up button | - successfuly sign up
5.1- verify create invalid ID number
steps | action | expected | status | test data | req.id | bug.id
5.1.1 | open ( website page/app) | - website opened | pass | mail: helmyahmed1993@gmail.com pass: 123456#Ah (min. 8 ch. with capital letter and symbol) ID : 29306 | TS1_TC5.1
5.1.2 | click on sign up button | - redirect to sign up page
5.1.3 | write your valid mail | - mobile number is entered
5.1.4 | click on continue button | - redirect to verification page
5.1.5 | wait for pin msg sent to ur mail | - pin msg sent
5.1.6 | enter sent code in code field | - filled in with pin code
5.1.7 | click on verify button | - redirect to next page
5.1.8 | create your password | - password field is filled in entered pass.
5.1.9 | rewrite your choosen pass. in confirm pass. field | - confirm password field is filled with pass.
5.1.10 | select remember me option | - remember me option is selected
5.1.11 | click on continue button | - redirect to ID num. page
5.1.12 | enter your invalid id number | - invalid id is entered
5.1.13 | click on sign up button | - error msg. wrong id
6- verify I dont have id number function
steps | action | expected | status | test data | req.id | bug.id
6.1 | open ( website page/app) | - website opened |  | mail: helmyahmed1993@gmail.com pass: 123456#Ah (min. 8 ch. with capital letter and symbol) ID : 29306041522289 | TS1_TC6
6.2 | click on sign up button | - redirect to sign up page
6.3 | write your valid mail | - mobile number is entered
6.4 | click on continue button | - redirect to verification page
6.5 | wait for pin msg sent to ur mail | - pin msg sent
6.6 | enter sent code in code field | - filled in with pin code
6.7 | click on verify button | - redirect to next page
6.8 | create your password | - password field is filled in entered pass.
6.9 | rewrite your choosen pass. in confirm pass. field | - confirm password field is filled with pass.
6.1 | select remember me option | - remember me option is selected
6.11 | click on continue button | - redirect to ID num. page
6.12 | click on I dont have id number button | - redirect to parent ID num. page
6.13 | enter your parent id number | - parent id num. is entered
6.14 | click on sign up button | - successfuly sign up
6.1- verify I dont have id number function with empty id
steps | action | expected | status | test data | req.id | bug.id
6.1.1 | open ( website page/app) | - website opened |  | mail: helmyahmed1993@gmail.com pass: 123456#Ah (min. 8 ch. with capital letter and symbol) ID : empty | TS1_TC6
6.1.2 | click on sign up button | - redirect to sign up page
6.1.3 | write your valid mail | - mobile number is entered
6.1.4 | click on continue button | - redirect to verification page
6.1.5 | wait for pin msg sent to ur mail | - pin msg sent
6.1.6 | enter sent code in code field | - filled in with pin code
6.1.7 | click on verify button | - redirect to next page
6.1.8 | create your password | - password field is filled in entered pass.
6.1.9 | rewrite your choosen pass. in confirm pass. field | - confirm password field is filled with pass.
6.1.10 | select remember me option | - remember me option is selected
6.1.11 | click on continue button | - redirect to ID num. page
6.1.12 | click on I dont have id number button | - redirect to parent ID num. page
6.1.13 | let your parent id number empty | - parent id num. field is empty
6.1.14 | click on sign up button | - error msg. with enter id

## 2-sign in
- Test suite : sign in
- Test suite ID : TS2
- Environment : (windows - android - IOS)
- pre-condition : 1-open URL / app 2- sign up
1- verify sign in button with valid data
steps | action | expected | status | test data | req.id | bug.id
1.1 | open sign in page | - sign in page is opened | pass | mail : helmyahmed1993@gmail.com (valid mail) pass: 123456#Ah (min. 8 ch. with capital letter and symbol) | TS2_TC1
1.2 | enter your registered mail | - registered mail is written
1.3 | enter your valid password | - password is written
1.4 | click on sign in button | - sign in successfuly and redirect to home page
1.1- verify sign in button with invalid data
steps | action | expected | status | test data | req.id | bug.id
1.1.1 | open sign in page | - sign in page is opened | pass | mail : helmyahmed1993 pass: 1234 | TS2_TC1.1
1.1.2 | enter invalid mail | - registered mail is written
1.1.3 | enter invalid password | - password is written
1.1.4 | click on sign in button | - wrong msg with invalid mail or password
1.2- verify sign in button with empty data
steps | action | expected | status | test data | req.id | bug.id
1.2.1 | open sign in page | - sign in page is opened | pass |  | TS2_TC1.2
1.2.2 | let mail field empty | - mobile number field empty
1.2.3 | let password field empty | - password field empty
1.2.4 | click on sign in button | - wrong msg with empty data please enter your mail and pass.
2- verify first use after sign in
steps | action | expected | status | test data | req.id | bug.id
2.1 | click on sign in button | - sign in successfuly and redirect to why using tap cash !! |  |  | TS2_TC2
2.2 | select your prefered options | - options selected
2.3 | click on next or skip button | - redirect to fill in your profile data page
2.1- verify first use with fill in your profile data page
steps | action | expected | status | test data | req.id | bug.id
2.1.1 | click on sign in button | - sign in successfuly and redirect to why using tap cash !! |  | full name: ahmed helmy nick name : ahmed mobile: 01016974716 | TS2_TC2.1
2.1.2 | select your prefered options | - options selected
2.1.3 | click on next or skip button | - redirect to fill in your profile data page
2.1.4 | enter your full name | - name is entered
2.1.5 | enter your nick name | - nick name is entered
2.1.6 | enter your mobile number | - mobile number is entered
2.1.7 | click on continue button | - redirect to create private pin
2.2- verify first use with fill in your profile data page with invalid data
steps | action | expected | status | test data | req.id | bug.id
2.1.1 | click on sign in button | - sign in successfuly and redirect to why using tap cash !! |  | full name: 1545 nick name : ahmed mobile: 01016 | TS2_TC2.2
2.1.2 | select your prefered options | - options selected
2.1.3 | click on next or skip button | - redirect to fill in your profile data page
2.1.4 | enter your invalid value | - invalid value is entered
2.1.5 | enter your nick name | - nick name is entered
2.1.6 | enter invalid mobile number | - mobile number is entered
2.1.7 | click on continue button | - error msg with please enter your valid registered number
3- verify create PIN page
steps | action | expected | status | test data | req.id | bug.id
3.1 | click on sign in button | - sign in successfuly and redirect to why using tap cash !! |  | PIN: 1234 full name: ahmed helmy nick name : ahmed mobile: 01016974716 | TS2_TC3
3.2 | select your prefered options | - options selected
3.3 | click on next or skip button | - redirect to fill in your profile data page
3.4 | enter your full name | - name is entered
3.5 | enter your nick name | - nick name is entered
3.6 | enter your mobile number | - mobile number is entered
3.7 | click on continue button | - redirect to create private pin
3.8 | write private four pin code from your choice | - private pin is written
3.9 | click on continue button | - redirect to finger print page
3.1- verify continue button without write PIN
steps | action | expected | status | test data | req.id | bug.id
3.1.1 | click on sign in button | - sign in successfuly and redirect to why using tap cash !! |  | full name: ahmed helmy nick name : ahmed mobile: 01016974716 pin : empty | TS2_TC3.1
3.1.2 | select your prefered options | - options selected
3.1.3 | click on next or skip button | - redirect to fill in your profile data page
3.1.4 | enter your full name | - name is entered
3.1.5 | enter your nick name | - nick name is entered
3.1.6 | enter your mobile number | - mobile number is entered
3.1.7 | click on continue button | - redirect to create private pin
3.1.8 | let private four pin code empty | - private pin is empty
3.1.9 | click on continue button | - error msg with please enter your private pin
4- verify set your fingerprint function
steps | action | expected | status | test data | req.id | bug.id
4.1 | click on sign in button | - sign in successfuly and redirect to why using tap cash !! |  | PIN: 1234 full name: ahmed helmy nick name : ahmed mobile: 01016974716 | TS2_TC4
4.2 | select your prefered options | - options selected
4.3 | click on next or skip button | - redirect to fill in your profile data page
4.4 | enter your full name | - name is entered
4.5 | enter your nick name | - nick name is entered
4.6 | enter your mobile number | - mobile number is entered
4.7 | click on continue button | - redirect to create private pin
4.8 | write private four pin code from your choice | - private pin is written
4.9 | click on continue button | - redirect to finger print page
4.1.10 | set your fingerprint correctly | - finger print is registered
4.11 | click on next button | - redirect to face recognation page
4.1- verify skip without set your fingerprint function
steps | action | expected | status | test data | req.id | bug.id
4.1.1 | click on sign in button | - sign in successfuly and redirect to why using tap cash !! |  | PIN: 1234 full name: ahmed helmy nick name : ahmed mobile: 01016974716 | TS2_TC4
4.1.2 | select your prefered options | - options selected
4.1.3 | click on next or skip button | - redirect to fill in your profile data page
4.1.4 | enter your full name | - name is entered
4.1.5 | enter your nick name | - nick name is entered
4.1.6 | enter your mobile number | - mobile number is entered
4.1.7 | click on continue button | - redirect to create private pin
4.1.8 | write private four pin code from your choice | - private pin is written
4.1.9 | click on continue button | - redirect to finger print page
4.1.10 | click on skip button without set fingerprint | - redirect to face recognation page
5- verify set your face recognation function
steps | action | expected | status | test data | req.id | bug.id
5.1 | click on sign in button | - sign in successfuly and redirect to why using tap cash !! |  | PIN: 1234 full name: ahmed helmy nick name : ahmed mobile: 01016974716 | TS2_TC5
5.2 | select your prefered options | - options selected
5.3 | click on next or skip button | - redirect to fill in your profile data page
5.4 | enter your full name | - name is entered
5.5 | enter your nick name | - nick name is entered
5.6 | enter your mobile number | - mobile number is entered
5.7 | click on continue button | - redirect to create private pin
5.8 | write private four pin code from your choice | - private pin is written
5.9 | click on continue button | - redirect to finger print page
5.1 | set your fingerprint correctly | - finger print is registered
5.11 | click on next button | - redirect to face recognation page
5.12 | set your face with qr scan | - face recognation is registered
5.13 | click on submit button | - redirect to congratulation msg then home page

## 3-forget password
- Test suite : forget password
- Test suite ID : TS3
- Environment : (windows - android - IOS)
- pre-condition : 1-open URL / app 2- sign up
1- verify forget password function
steps | action | expected | status | test data | req.id | bug.id
1.1 | open sign in page | - sign in page is opened |  | mail : helmyahmed1993@gmail.com (valid mail) sent ver. code : 1234 | TS3_TC1
1.2 | enter your registered mail | - registered mail is written
1.3 | click on forget password button if you forget it | - redirect to forget password page
1.4 | click on send button | - redirect to sent verification code page
1.5 | write sent verification code | - verification code is written
1.6 | click on verify button | - redirect to create new password page
1.1- verify forget password function with write invalid sent verification code
steps | action | expected | status | test data | req.id | bug.id
1.1.1 | open sign in page | - sign in page is opened |  | mail : helmyahmed1993@gmail.com (valid mail) invalid sent ver. code : 0000 | TS3_TC1.1
1.1.2 | enter your registered mobile number | - registered mobile number is written
1.1.3 | click on forget password button if you forget it | - redirect to forget password page
1.1.4 | click on send button | - redirect to sent verification code page
1.1.5 | write invalid verification code | - invalid verification code is written
1.1.6 | click on verify button | - error msg with error code
2- verify create new password function
steps | action | expected | status | test data | req.id | bug.id
2.1 | open sign in page | - sign in page is opened |  | mail : helmyahmed1993@gmail.com (valid mail) sent ver. code : 1234 pass: 123456#Ah (min. 8 ch. with capital letter and symbol) | TS3_TC2
2.2 | enter your registered mobile number | - registered mobile number is written
2.3 | click on forget password button if you forget it | - redirect to forget password page
2.4 | click on send button | - redirect to sent verification code page
2.5 | write sent verification code | - verification code is written
2.6 | click on verify button | - redirect to create new password page
2.7 | write valid new password not less than eight numbers and characters including special character | -new pass. is written
2.8 | write confirm new password | - confirm new pass. is written
2.9 | click on confirm button | - redirect to congratulation page then home page
2.1- verify create new password function with invalid password
steps | action | expected | status | test data | req.id | bug.id
2.1.1 | open sign in page | - sign in page is opened |  | mail : helmyahmed1993@gmail.com (valid mail) sent ver. code : 1234 invalid pass: 000 valid should include (min. 8 ch. with capital letter and symbol) | TS3_TC2.1
2.1.2 | enter your registered mobile number | - registered mobile number is written
2.1.3 | click on forget password button if you forget it | - redirect to forget password page
2.1.4 | click on send button | - redirect to sent verification code page
2.1.5 | write sent verification code | - verification code is written
2.1.6 | click on verify button | - redirect to create new password page
2.1.7 | write invalid new password less than eight numbers and characters including special character | -new pass. is written
2.1.8 | write confirm invalid password | - confirm new pass. is written
2.1.9 | click on confirm button | - error msg with invalid pass. please insert correct one

## 4-home page
- Test suite : home page
- Test suite ID : TS5
- Environment : (windows - android - IOS)
- pre-condition : 1-open URL / app 2- sign up 3- sign in
1- check notification symbol and back icon to home page
steps | action | expected | status | test data | req.id | bug.id
1.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS5_TC1
1.2 | click on notification sympol | - redirect to page of notification of transactions
1.3 | click on back icon | - redirect to home page
2- check (requist button) from send function with valid id and amount
steps | action | expected | status | test data | req.id | bug.id
2.1 | click on sign in button | - sign in successfuly and redirect to home page |  | - id : 29305041200021 - amount money : from 1 LE to 15000 LE | TS5_TC2
2.2 | click on send button | - small page of select how to add money to your account
2.3 | select send to tap cash friends | - redirect to page to insert id number
2.4 | enter valid id num. | - valid id is entered
2.5 | click on continue button to complete the process | - redirect to page to insert amount money
2.6 | click on requist button to complete the process | - msg. of amount requisted successfuly
2.1- check (send button) from send function with valid id and amount
steps | action | expected | status | test data | req.id | bug.id
2.1.1 | click on sign in button | - sign in successfuly and redirect to home page |  | - id : 29305041200021 - amount money : from 1 LE to 15000 LE | TS5_TC2.1
2.1.2 | click on send button | - small page of select how to add money to your account
2.1.3 | select send to tap cash friends | - redirect to page to insert id number
2.1.4 | enter valid id num. | - valid id is entered
2.1.5 | click on continue button to complete the process | - redirect to page to insert amount money
2.1.6 | click on send button to complete the process | - msg. of amount sent successfuly
2.2- check (send and requist button) from send function with invalid id and valid amount
steps | action | expected | status | test data | req.id | bug.id
2.2.1 | click on sign in button | - sign in successfuly and redirect to home page |  | - id : 29305041 - amount money : from 1 LE to 15000 LE | TS5_TC2.2
2.2.2 | click on send button | - small page of select how to add money to your account
2.2.3 | select send to tap cash friends | - redirect to page to insert id number
2.2.4 | enter invalid id less than 16 num. | - invalid id is entered
2.2.5 | click on continue button to complete the process | - error msg. of invalid id
2.3- check (send and requist button) from send function with valid id and invalid amount
steps | action | expected | status | test data | req.id | bug.id
2.3.1 | click on sign in button | - sign in successfuly and redirect to home page |  | - id : 2930504112358964 - amount money : less 1 LE or more than 15000 LE | TS5_TC2.3
2.3.2 | click on send button | - small page of select how to add money to your account
2.3.3 | select send to tap cash friends | - redirect to page to insert id number
2.3.4 | enter valid id with16 num. | - valid id is entered
2.3.5 | enter invalid amount money less than 1 LE or more than 15000 LE | - invalid amount entered
2.3.6 | click on continue button to complete the process | - error msg. of invalid id
3- check smart card function with valid pin and amount
steps | action | expected | status | test data | req.id | bug.id
3.1 | click on sign in button | - sign in successfuly and redirect to home page |  | - PIN : 1234 - amount money : from 1 LE to 15000 LE | TS5_TC3
3.2 | click on smart card button | - redirect to page of online payment card
3.3 | click on export card | - redirect to page to insert your PIN
3.4 | enter valid PIN num. | - valid PIN num. is entered then redirect to insert the required amount money to export
3.5 | insert the valid required amount money to export | - valid required amount money is entered
3.6 | click on export card to confirm the process | - msg. of copy card that valid for 24 hour to use on app.
3.1- check smart card function with invalid pin
steps | action | expected | status | test data | req.id | bug.id
3.1.1 | click on sign in button | - sign in successfuly and redirect to home page |  | - PIN : 12 | TS5_TC3.1
3.1.2 | click on smart card button | - redirect to page of online payment card
3.1.3 | click on export card | - redirect to page to insert your PIN
3.1.4 | enter invalid PIN num. | - invalid PIN num. is entered
3.1.5 | click on continue button | - error msg. with enter your valid pin
3.2- check smart card function with valid pin and invalid amount
steps | action | expected | status | test data | req.id | bug.id
3.2.1 | click on sign in button | - sign in successfuly and redirect to home page |  | - PIN : 1234 - amount money : less 1 LE or more than 15000 LE | TS5_TC3.2
3.2.2 | click on smart card button | - redirect to page of online payment card
3.2.3 | click on export card | - redirect to page to insert your PIN
3.2.4 | enter valid PIN num. | - valid PIN num. is entered then redirect to insert the required amount money to export
3.2.5 | insert the invalid required amount money | - invalid required amount money is entered
3.2.6 | click on export card to confirm the process | - error msg. of enter valid amount
4- check view all active cards function
steps | action | expected | status | test data | req.id | bug.id
4.1 | click on sign in button | - sign in successfuly and redirect to home page |  | - PIN : 1234 | TS5_TC4
4.2 | click on smart card button | - redirect to page of online payment card
4.3 | click on view all active cards | - redirect to page to insert your PIN
4.4 | enter valid PIN num. | - valid PIN num. is entered
4.5 | click on continue button | - redirect to page of view all active cards
4.1- check view all active cards function with invalid pin
steps | action | expected | status | test data | req.id | bug.id
4.1.1 | click on sign in button | - sign in successfuly and redirect to home page |  | - PIN : 12 | TS5_TC4.1
4.1.2 | click on smart card button | - redirect to page of online payment card
4.1.3 | click on view all active cards | - redirect to page to insert your PIN
4.1.4 | enter invalid PIN num. | - invalid PIN num. is entered
4.1.5 | click on continue button | - error msg. with enter valid pin
5- check (you get cash back) function
steps | action | expected | status | test data | req.id | bug.id
5.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS5_TC5
5.2 | click on you get cash back button | - redirect to page of notifications transaction displayed
6- check services (internet) function with valid amount and pin
steps | action | expected | status | test data | req.id | bug.id
6.1 | click on sign in button | - sign in successfuly and redirect to home page |  | amount > 0 pin = 1234 | TS5_TC6
6.2 | click on services (internet) function | - redirect to page of pay internet bill
6.3 | add amount of money for payment | - amount added
6.4 | click on continue button | - msg. of confirm payment with valid info. account
6.5 | click on confirm payment button | - redirect to page of enter your pin
6.6 | enter your valid pin | - valid pin is entered
6.7 | click on confirm payment button | - msg. of bill paid succsessful
6.1- check services (internet) function with invalid amount
steps | action | expected | status | test data | req.id | bug.id
6.1.1 | click on sign in button | - sign in successfuly and redirect to home page |  | amount = 0 | TS5_TC6.1
6.1.2 | click on services (internet) function | - redirect to page of pay internet bill
6.1.3 | add amount of money for payment | - amount is zero
6.1.4 | click on continue button | - error msg. of enter valid amount
6.2- check services (internet) function with invalid pin
steps | action | expected | status | test data | req.id | bug.id
6.2.1 | click on sign in button | - sign in successfuly and redirect to home page |  | amount > 0 pin = 12 | TS5_TC6.2
6.2.2 | click on services (internet) function | - redirect to page of pay internet bill
6.2.3 | add amount of money for payment | - amount added
6.2.4 | click on continue button | - msg. of confirm payment with valid info. account
6.2.5 | click on confirm payment button | - redirect to page of enter your pin
6.2.6 | enter your invalid pin | - error msg. of enter valid pin
7- check services (donatiors) function
steps | action | expected | status | test data | req.id | bug.id
7.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS5_TC7
7.2 | click on donatiors function | - redirect to page of Charities
8- check online payment function with invalid pin
steps | action | expected | status | test data | req.id | bug.id
8.1 | click on sign in button | - sign in successfuly and redirect to home page |  | amount > 0 pin = 12 | TS5_TC8
8.2 | click on online payment function | - redirect to page of online payment
8.3 | enter your valid item data | - data added
8.4 | click on pay button | - redirect to page of enter your pin
8.5 | enter invalid pin | - error msg. of enter valid pin
8.6 | click on confirm payment button | - error msg. of enter valid pin
9- verify QR function with valid pin
steps | action | expected | status | test data | req.id | bug.id
9.1 | click on sign in button | - sign in successfuly and redirect to home page |  | pin = 1234 | TS5_TC9
9.2 | click on QR function function | - redirect to page of QR function
9.3 | scan your QR code/photo | - code scaned then redirect to order page
9.4 | click on confirm payment button | - redirect to page of enter your pin
9.5 | enter valid pin | - valid pin is entered
9.6 | click on confirm payment button | - paid successfuly
9.1- verify QR function with invalid pin
steps | action | expected | status | test data | req.id | bug.id
9.1.1 | click on sign in button | - sign in successfuly and redirect to home page |  | pin = 00 | TS5_TC9.1
9.1.2 | click on QR function function | - redirect to page of QR function
9.1.3 | scan your QR code/photo | - code scaned then redirect to order page
9.1.4 | click on confirm payment button | - redirect to page of enter your pin
9.1.5 | enter invalid pin | - invalid pin is entered
9.1.6 | click on confirm payment button | - error msg. with enter valid pin

## 5-wallet
- Test suite : wallet
- Test suite ID : TS4
- Environment : (windows - android - IOS)
- pre-condition : 1-open URL / app 2- sign up 3- sign in
1- verify Add function
steps | action | expected | status | test data | req.id | bug.id
1.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS4_TC1
1.2 | click on add button | - redirect to next page to connect new card
1.3 | click on connect cart | - redirect to add new card page
2- verify wallet category
steps | action | expected | status | test data | req.id | bug.id
1.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS4_TC2
1.2 | click on wallet category | - redirect to e-wallet page
3- verify e-wallet page (Add new card) with valid data
steps | action | expected | status | test data | req.id | bug.id
3.1 | click on sign in button | - sign in successfuly and redirect to home page |  | - card number : 1234-2563-8564-9825 (valid 16 numbers) -expire date : 02/25 (valid month and year) - cvv : 123 (valid 3 numbers) | TS4_TC3
3.2 | click on wallet category | - redirect to e-wallet page
3.3 | click on add new card | - redirect to add new card page
3.4 | enter your card number | - filled with card number
3.5 | enter expire date of your card | - filled with expire date card
3.6 | enter CVV card number | - filled with cvv number
3.7 | click on continue button | - card added successfuly msg.
3.1- verify e-wallet page (Add new card) with invalid data
steps | action | expected | status | test data | req.id | bug.id
3.1.1 | click on sign in button | - sign in successfuly and redirect to home page |  | - card number : 0000-0000-0000-0000 (valid 16 numbers) -expire date : 02/2023 (valid month and year) - cvv : 12 (valid 3 numbers) | TS4_TC3.1
3.1.2 | click on wallet category | - redirect to e-wallet page
3.1.3 | click on add new card | - redirect to add new card page
3.1.4 | enter your invalid card number | - filled with card number
3.1.5 | enter invalid expire date of your card | - filled with expire date card
3.1.6 | enter CVV card number | - filled with cvv number
3.1.7 | click on continue button | - error msg. invalid data
3.2- verify e-wallet page (Add new card) with empty data
steps | action | expected | status | test data | req.id | bug.id
3.2.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS4_TC3.2
3.2.2 | click on wallet category | - redirect to e-wallet page
3.2.3 | click on add new card | - redirect to add new card page
3.2.4 | let card number field empty | - field is empty
3.2.5 | let date field empty | - field is empty
3.2.6 | let CVV number field empty | - field is empty
3.2.7 | click on continue button | - error msg. please enter card data
4- verify e-wallet page (edite limit) function
steps | action | expected | status | test data | req.id | bug.id
4.1 | click on sign in button | - sign in successfuly and redirect to home page |  | - amount money : from 1 LE to 15000 LE | TS4_TC4
4.2 | click on wallet category | - redirect to e-wallet page
4.3 | click on edite button | - redirect to change limit card page
4.4 | modify your limit | - limit cash and transaction is modified
4.5 | click on save changes button | - changes saved and redirect to e-wallet page
5- verify e-wallet page (Add money) function
steps | action | expected | status | test data | req.id | bug.id
5.1 | click on sign in button | - sign in successfuly and redirect to home page |  | - amount money : from 1 LE to 15000 LE | TS4_TC5
5.2 | click on wallet category | - redirect to e-wallet page
5.3 | click on top up amount button | - msg. with your available cards to choose from them
5.4 | choose your card that want to add with it | - wanted card is choosen and redirect to add money page
5.5 | select the wanted amount then click on top up amount button | - required money is written then msg. with amount money is added
5.1- verify e-wallet page (Add money) function without data
steps | action | expected | status | test data | req.id | bug.id
5.1.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS4_TC5.1
5.1.2 | click on wallet category | - redirect to e-wallet page
5.1.3 | click on top up amount button | - msg. with your available cards to choose from them
5.1.4 | choose your card that want to add with it | - wanted card is choosen and redirect to add money page
5.1.5 | let the field of top up amount is empty without write amount of money | - required money field is empty
5.1.6 | click on top up button | - msg. with please insert required data
6- verify e-wallet page (withdraw) function
steps | action | expected | status | test data | req.id | bug.id
6.1 | click on sign in button | - sign in successfuly and redirect to home page |  | - amount money : from 1 LE to 15000 LE | TS4_TC6
6.2 | click on wallet category | - redirect to e-wallet page
6.3 | click on refund button | - msg. with your available cards to choose from them
6.4 | choose your card that want to add with it | - wanted card is choosen and redirect to add money page
6.5 | select the wanted amount then click on refund amount button | - required money is written then msg. with amount money is refunded
7- verify e-wallet page (card symbol) delete function
steps | action | expected | status | test data | req.id | bug.id
7.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS4_TC7
7.2 | click on wallet category | - redirect to e-wallet page
7.3 | click on card symbol | - open small page with card data and function of delete card
7.4 | click on delete button | - msg. with delete this card ?
7.5 | click on yes to delete this card | - this selected card is deleted
7.1- verify e-wallet page (card symbol) cancel delete function
steps | action | expected | status | test data | req.id | bug.id
7.1.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS4_TC7.1
7.1.2 | click on wallet category | - redirect to e-wallet page
7.1.3 | click on card symbol | - open small page with card data and function of delete card
7.1.4 | click on delete button | - msg. with delete this card ?
7.1.5 | click on cancel | - this selected card is not deleted then return to e-wallet page

## 6-dash board
- Test suite : dash board
- Test suite ID : TS6
- Environment : (windows - android - IOS)
- pre-condition : 1-open URL / app 2- sign up 3- sign in
1- check dashboard in category bar
steps | action | expected | status | test data | req.id | bug.id
6.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS6_TC1
6.2 | click on dashboard function | - redirect to page of dashboard to display dashboard graph of your transactions

## 7-more
- Test suite : more
- Test suite ID : TS7
- Environment : (windows - android - IOS)
- pre-condition : 1-open URL / app 2- sign up 3- sign in
1- check more function in category bar (privacy policy)
steps | action | expected | status | test data | req.id | bug.id
1.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS7_TC1
1.2 | click on more function | - more list is opened
1.3 | click on privacy policy function | - redirect to privacy policy page to read it
2- check more function in category bar (gifts)
steps | action | expected | status | test data | req.id | bug.id
2.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS7_TC2
2.2 | click on more function | - more list is opened
2.3 | click on gifts button | - redirect to gifts page to spin and win
3- check more function in category bar (logout)
steps | action | expected | status | test data | req.id | bug.id
3.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS7_TC3
3.2 | click on more function | - more list is opened
3.3 | click on logout function | - redirect to login to your account page
4- check more function in category bar (cash back)
steps | action | expected | status | test data | req.id | bug.id
4.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS7_TC4
4.2 | click on more function | - more list is opened
4.3 | click on cash back button | - redirect to cash back page to convert your points
5- check more function in category bar (bill reminder)
steps | action | expected | status | test data | req.id | bug.id
5.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS7_TC5
5.2 | click on more function | - more list is opened
5.3 | click on requists button | - redirect to bill reminder page
5.4 | enter required data | - required data is entered
5.5 | click on ok button | - requist is registed
6- check more function in category bar (group payment)
steps | action | expected | status | test data | req.id | bug.id
6.1 | click on sign in button | - sign in successfuly and redirect to home page |  |  | TS7_TC6
6.2 | click on more function | - more list is opened
6.3 | click on group payment button | - redirect to group payment page
6.4 | click on create group button | - redirect to the next page
6.5 | enter required data | - required data is entered
6.6 | click on continue button | - redirect to select amount page
6.7 | click on pay button | - bill paid successfuly

## test summary report
test summary report
Principles and steps followed during the project :
1- Principle | - early testing
2- main activities | - test planning - test designing - test execution
3- test types | - functional testing (black box) - confirmation testing
4- test techniques | - static testing (by find bugs before execute s.w.)
5- test levels | - integration testing - system testing
6- test cases | - design - execution
7- manual API testing | - Postman tool
8- Bugs | - design Bug report